## Tabelle1
ML-Tasks | Status | Done-Date | Deadline | Comment
Git- creat & Invite | Done | 2025-04-14 | 2025-04-25
Abstract of topic and main reference | Done | 2025-04-20 | 2025-05-01
implementation env | Done | 2025-04-20
paper research | Done | 2025-04-20
summary (one paragraph) of related papers | Done | 2025-04-20
Impact to my paper | Done | 2025-04-20
Upload a bib file including a summary section | Done | 2025-05-07 |  | Prof said has to write a summary even if there is a realted work in tex file
get familiar with SVMs | Not yet |  |  | more svms
implement first test scenarios | Done | 2025-04-20
Get familar with openCV | Pending | ***** |  | line following transfer data ansd dmap
Initial Version of the Model | Done | 2025-04-25 | **** | UI/UX Ai model app presented and ready
raw paper incl. Bullet points and refined references | Done | 2025-05-07 | 2025-05-09
Define Evaluation and tooling | Done | 2025-05-07
Analysis of data and alternative data sets | pending
More MATHS & Other Regrissions | Not yet |  | 2025-05-16 | maths , all regrission , performance , optimiaziaiton with svms
version including main figures and first evaluation | pending |  | 2025-05-16
deep evaluation and tooling | pending |  | 2025-05-23
version including all input | Done |  | 2025-05-30
First version of presentation slides | pending |  | 2025-05-30
update of paper Max (5 Pages) | pending |  | 2025-06-06
ML presentation | Tbd |  | Tbd