## Tabelle1
ML-Tasks | Status | Done-Date | Deadline | Comment
Git- creat & Invite | Done | 2025-04-14 | 2025-04-25
Abstract of topic and main reference | Done | 2025-04-20 | 2025-05-01
implementation env | Done | 2025-04-20 | 2025-05-01
paper research | Done | 2025-04-20 | 2025-05-01
summary (one paragraph) of related papers | Done | 2025-04-20 | 2025-05-01
Impact to my paper | pending |  | 2025-05-01
Upload a bib file including a summary section | pending |  | 2025-05-01
get familiar with SVMs | Done | 2025-04-20 | 2025-05-01
implement first test scenarios | pending |  | 2025-05-01
Get familar with openCV | Done | 2025-04-20 | 2025-05-01
Initial Version of the Model | Done | 2025-04-25 | ****
raw paper incl. Bullet points and refined references | pending |  | 2025-05-09
Define Evaluation and tooling | pending |  | 2025-05-09
Analysis of data and alternative data sets | pending |  | 2025-05-09
version including main figures and first evaluation | pending |  | 2025-05-16
deep evaluation and tooling | pending |  | 2025-05-23
version including all input | Done |  | 2025-05-30
First version of presentation slides | pending |  | 2025-05-30
update of paper Max (5 Pages) | pending |  | 2025-06-06
ML presentation | Tbd |  | Tbd